## Feuil2 (hidden)
ESF1 | BAP | COMPLEXE
BJF1 | KLP1 | SUD
BKF1 | KLF1 | NORD
BOF1 | KLF2
BOF2 | KLF3 | COMPLEXE | BAF 3
BRF1 | KLF4 | CENTRE | BAF T1
BTF1 | NNF1 | NORD | BAF T2
BTF2 | ITF1 |  | KB 4-5
EKF1 | DKF1 |  | KB GAS
EKF2 | DKF2 |  | KB NORD
EKF3 | SIRONA |  | KL
ESP 2 | BVF1 |  | EBOME
ESP1 | BVF2 |  | KF7
INF1 | BVF3 |  | KF8
KCF1 | BVF4 |  | KF9
KCF2 | AKF1
KCF3 | ACF1
KEF1 | ACF2
KNF1 | ASP1
VT | ASP2
DIF1
DIF2
OAK
ENF1
LSF1

## RDRE
PID CENSUS
Plateform N° | Plateforms | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[6 empty] | 100% |  | 100% | 100%
1 | BAP | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
|  | Dessaleurs | CM-KO-72N-015-001002 | OK | OK |  | 100% |  | 0% | 0%
|  | Ballon FWKO | CM-KO-72N-015-001003 | N/A |  |  | 0% |  | 0% | 0%
|  | Slug catcher et depart huile | CM-KO-72N-015-001004 | OK | OK |  | 100% |  | 0% | 0%
|  | Chaudières | CM-KO-72N-015-001005 | N/A |  |  | 0% |  | 0% | 0%
|  | Compression | CM-KO-72N-015-001006 | N/A |  |  | 0% |  | 0% | 0%
|  | Traitement fuel gas | CM-KO-72N-015-001007 | N/A |  |  | 0% |  | 0% | 0%
|  | Rechauffage Fuel gas | CM-KO-72N-015-001008 | N/A |  |  | 0% |  | 0% | 0%
|  | Reseau injection eau | CM-KO-72N-015-001009 | N/A |  |  | 0% |  | 0% | 0%
|  | Reseau eau | CM-KO-72N-015-001010 | OK | OK |  | 100% |  | 0% | 0%
|  | Reseau eau de mer | CM-KO-72N-015-001011 | OK | OK |  | 100% |  | 0% | 0%
|  | Traitement eau-decanteur | CM-KO-72N-015-001012 | OK | OK |  | 100% |  | 0% | 0%
|  | Traitement eau-bac tampon | CM-KO-72N-015-001013 | OK | OK |  | 100% |  | 0% | 0%
|  | Traitement eau-flottateur | CM-KO-72N-015-001014 | N/A |  |  | 0% |  | 0% | 0%
|  | PID Ecrémeur | CM-KO-72N-015-001015 | N/A |  |  | 0% |  | 0% | 0%
|  | Circuit purges | CM-KO-72N-015-001016 | N/A |  |  | 0% |  | 0% | 0%
|  | Réseau Torche | CM-KO-72N-015-001017 | N/A |  |  | 0% |  | 0% | 0%
|  | Réseau Incendie | CM-KO-72N-015-001018 | N/A |  |  | 0% |  | 0% | 0%
|  | Air service et air instrument | CM-KO-72N-015-001019 | N/A |  |  | 0% |  | 0% | 0%
|  | Diesel oil | CM-KO-72N-015-001020 | N/A |  |  | 0% |  | 0% | 0%
|  | Echangeurs | CM-KO-72N-015-001021 | OK | OK |  | 100% |  | 0% | 0%
|  | Turbo generateurs | CM-KO-72N-015-001022 | N/A |  |  | 0% |  | 0% | 0%
|  | Groupe turbo pompes | CM-KO-72N-015-001023 | N/A |  |  | 0% |  | 0% | 0%
|  | Passerelle de liaison vers KLP1 | CM-KO-72N-015-001024 | OK | OK |  | 100% |  | 0% | 0%
|  | Eau Industrielle | CM-KO-72N-015-001025 | N/A |  |  | 0% |  | 0% | 0%
|  | PID cuve de purges | CM-KO-72N-015-001026 | OK | OK |  | 100% |  | 0% | 0%
|  | CFU 3504 & 3503 | CM-KO-72N-015-001027 | OK | OK |  | 100% |  | 0% | 0%
|  | Traitement eau-Hydrocyclone ID3523 | CM-KO-72N-015-001028 | OK | OK |  | 100% |  | 0% | 0%
|  | Traitement eau-Hydrocyclones | CM-KO-72N-015-001029 | OK | OK |  | 100% |  | 0% | 0%
2 | KLP1 | Arrivees huile et gaz | CM-KO-72B-015-001101 | OK | NO |  | 0% |  | 0% | 0%
|  | Circuit huile | CM-KO-72B-015-001102 | OK | NO |  | 0% |  | 0% | 0%
|  | Ballon FWKO | CM-KO-72B-015-001103 | OK | NO |  | 0% |  | 0% | 0%
|  | Ballon de Torche | CM-KO-72B-015-001104 | N/A | NO |  | 0% |  | 0% | 0%
|  | Torche et events | CM-KO-72B-015-001105 | N/A | NO |  | 0% |  | 0% | 0%
|  | Pomperie | CM-KO-72B-015-001106 | N/A | NO |  | 0% |  | 0% | 0%
|  | Scrubber gas | CM-KO-72B-015-001107 | OK | NO |  | 0% |  | 0% | 0%
|  | Circuit purges | CM-KO-72B-015-001108 | N/A | NO |  | 0% |  | 0% | 0%
|  | Circuit gaz | CM-KO-72B-015-001109 | OK | NO |  | 0% |  | 0% | 0%
|  | Decanteur | CM-KO-72B-015-001110 | N/A | NO |  | 0% |  | 0% | 0%
|  | Reseau incendie | CM-KO-72B-015-001111 | OK | NO |  | 0% |  | 0% | 0%
|  | Reseau air instrumentation | CM-KO-72B-015-001112 | N/A | NO |  | 0% |  | 0% | 0%
|  | Refroidisseurs | CM-KO-72B-015-001113 | N/A | NO |  | 0% |  | 0% | 0%
|  | Passerelle de liaison vers BAP | CM-KO-72B-015-001114 | N/A | NO |  | 0% |  | 0% | 0%
|  | PID POMPES KOLEXP | CM-KO-72B-015-XXXXXX | OK | NO |  | 0% |  | 0% | 0%
|  | Passerelle de liaison vers KLF1 | CM-KO-72B-015-001115 | OK | NO |  | 0% |  | 0% | 0%
3 | KLF1 | Puits de production huile (typique) | CM-KO-72D-015-001201 | N/A | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-KO-72D-015-001202 | N/A | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-KO-72D-015-001203 | N/A | NO |  | 0% |  | 0% | 0%
|  | Arrivees huile et gaz | CM-KO-72D-015-001204 | OK | NO |  | 0% |  | 0% | 0%
|  | Puits d'injection et de production gaz | CM-KO-72D-015-001205 | N/A | NO |  | 0% |  | 0% | 0%
|  | Manifold gaz | CM-KO-72D-015-001206 | OK | NO |  | 0% |  | 0% | 0%
|  | Injection eau (Typique) | CM-KO-72D-015-001207 | OK | NO |  | 0% |  | 0% | 0%
|  | Production eau | CM-KO-72D-015-001208 | N/A | NO |  | 0% |  | 0% | 0%
|  | Reseau Incendie | CM-KO-72D-015-001209 | N/A | NO |  | 0% |  | 0% | 0%
|  | Circuit purges | CM-KO-72D-015-001210 | N/A | NO |  | 0% |  | 0% | 0%
|  | Reseau air instrumentation | CM-KO-72D-015-001211 | N/A | NO |  | 0% |  | 0% | 0%
|  | Passerelle de liaison vers KLP1 | CM-KO-72D-015-001212 | N/A | NO |  | 0% |  | 0% | 0%
|  | Stockage demulsifiant | CM-KO-72D-015-001213 | N/A | NO |  | 0% |  | 0% | 0%
4 | KLF2 | Drains fermés | P260-04-GE205X-PID-7272 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-04-GE205X-PID-7226 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-04-GE205X-PID-7227 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-04-GE205X-PID-7276 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-04-GE205X-PID-7274 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-04-GE205X-PID-7223 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile | P260-04-GE205X-PID-7220 | NO | NO |  | 0% |  | 0% | 0%
5 | KLF3 | Air instrument | P260-07-GE205X-PID-7285 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-07-GE205X-PID-7282 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-7283 | NO | NO |  | 0% |  | 0% | 0%
|  | Event | P260-07-GE205X-PID-7281 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-07-GE205X-PID-7237 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-07-GE205X-PID-7286 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-07-GE205X-PID-7284 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-7233 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile | P260-07-GE205X-PID-7230 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-7234 | NO | NO |  | 0% |  | 0% | 0%
|  | Torche | P260-07-GE205X-PID-7280 | NO | NO |  | 0% |  | 0% | 0%
6 | KLF4 | Drains fermes et ballon d'event | P260-07-GE205X-PID-7292 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-7293 | NO | NO |  | 0% |  | 0% | 0%
|  | Eau d'injection | P260-07-GE205X-PID-7248 | NO | NO |  | 0% |  | 0% | 0%
|  | Events | P260-07-GE205X-PID-7291 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-07-GE205X-PID-7246 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-07-GE205X-PID-7247 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-07-GE205X-PID-7296 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-07-GE205X-PID-7294 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection de produits | P260-07-GE205X-PID-7297 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-7243 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile | P260-07-GE205X-PID-7240 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile 2 | P260-07-GE205X-PID-7240 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-7244 | NO | NO |  | 0% |  | 0% | 0%
7 | NNF1 | Export huile | P260-07-GE205X-PID-8916 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz lift | P260-07-GE205X-PID-8917 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection d'eau | P260-07-GE205X-PID-8918 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-8913 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits production gaz | P260-07-GE205X-PID-8910 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile | P260-07-GE205X-PID-8912 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits d'injection d'eau | P260-07-GE205X-PID-8911 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production 2 | P260-07-GE205X-PID-8915 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-07-GE205X-PID-8915 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-8914 | NO | NO |  | 0% |  | 0% | 0%
|  | Torche | P260-07-GE205X-PID-8960 | NO | NO |  | 0% |  | 0% | 0%
|  | Event | P260-07-GE205X-PID-8961 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-07-GE205X-PID-8962 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-8963 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-07-GE205X-PID-8964 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments et air instruments | P260-07-GE205X-PID-8966 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon er compresseur ARIEL | P260-07-GE205X-PID-8967 | NO | NO |  | 0% |  | 0% | 0%
|  | Compresseur et ballon d'air | P260-07-GE205X-PID-8968 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon gas lift | P260-07-GE205X-PID-8969 | NO | NO |  | 0% |  | 0% | 0%
8 | ITF1 | Air instrument 2 | P260-07-GE205X-PID-9265 | NO | NO |  | 0% |  | 0% | 0%
|  | Air instrument | P260-07-GE205X-PID-9265 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-07-GE205X-PID-9262 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-9263 | NO | NO |  | 0% |  | 0% | 0%
|  | Event | P260-07-GE205X-PID-9261 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-07-GE205X-PID-9216 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-07-GE205X-PID-9217 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-07-GE205X-PID-9264 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection de produits | P260-07-GE205X-PID-9267 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection d'eau | P260-07-GE205X-PID-9218 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-9213 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile 2 | P260-07-GE205X-PID-9213 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits production gaz | P260-07-GE205X-PID-9211 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits production d'huile | P260-07-GE205X-PID-9210 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits injection d'eau | P260-07-GE205X-PID-9212 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-9214 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-07-GE205X-PID-9215 | NO | NO |  | 0% |  | 0% | 0%
|  | Torche | P260-07-GE205X-PID-9260 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon et compresseur Ariel | P260-07-GE205X-PID-9268 | NO | NO |  | 0% |  | 0% | 0%
9 | DKF1 | Puits de production d'huile | CM-KOL72S-015-001005 | NO | NO |  | 0% |  | 0% | 0%
|  | Expedition huile | CM-KOL72S-015-001006 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-KOL72S-015-001007 | NO | NO |  | 0% |  | 0% | 0%
|  | Appareil de test | CM-KOL72S-015-001008 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit gas lift | CM-KOL72S-015-001009 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et gaz | CM-KOL72S-015-001010 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | CM-KOL72S-015-001011 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur DS1002 | CM-KOL72S-015-001012 | NO | NO |  | 0% |  | 0% | 0%
10 | BVF1 | Ballon de Torche | CM-BVM83B-015-000015 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit gas lift | CM-BVM83B-015-000012 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et drains | CM-BVM83B-015-000014 | NO | NO |  | 0% |  | 0% | 0%
|  | Gare de racleurs huile/gaz | CM-BVM83B-015-000007 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument | CM-BVM83B-015-000017 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection d'eau | CM-BVM83B-015-000018 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | CM-BVM83B-015-000013 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-BVM83B-015-000006 | NO | NO |  | 0% |  | 0% | 0%
|  | Pomperie | CM-BVM83B-015-000008 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile (typique) | CM-BVM83B-015-000005 | NO | NO |  | 0% |  | 0% | 0%
|  | Reseau incendie | CM-BVM83B-015-000016 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 1er etage | CM-BVM83B-015-000010 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 2ème etage | CM-BVM83B-015-000011 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-BVM83B-015-000009 | NO | NO |  | 0% |  | 0% | 0%
11 | BVF2 | Ballon de Torche | CM-ASO83D-015-001015 | NO | NO |  | 0% |  | 0% | 0%
|  | Scrubber gas lift | CM-ASO83D-015-001012 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et drains | CM-ASO83D-015-001014 | NO | NO |  | 0% |  | 0% | 0%
|  | Gare de racleurs | CM-ASO83D-015-001007 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument | CM-ASO83D-015-001016 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | CM-ASO83D-015-001013 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-ASO83D-015-001006 | NO | NO |  | 0% |  | 0% | 0%
|  | Pomperie | CM-ASO83D-015-001008 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile (typique) | CM-ASO83D-015-001005 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 1er etage | CM-ASO83D-015-001010 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 2ème etage | CM-ASO83D-015-001011 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-ASO83D-015-001009 | NO | NO |  | 0% |  | 0% | 0%
12 | BVF3 | Puits de production huile (typique) | CM-BAV83F-015-000105 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-BAV83F-015-000106 | NO | NO |  | 0% |  | 0% | 0%
|  | Gare de racleurs | CM-BAV83F-015-000107 | NO | NO |  | 0% |  | 0% | 0%
|  | Pomperie | CM-BAV83F-015-000108 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-BAV83F-015-000109 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 1er etage | CM-BAV83F-015-000110 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur 2ème etage | CM-BAV83F-015-000111 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | CM-BAV83F-015-000112 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit gas lift | CM-BAV83F-015-000113 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et drains | CM-BAV83F-015-000114 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon de Torche | CM-BAV83F-015-000115 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection d'eau et réseau incendie | CM-BAV83F-015-000116 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument | CM-BAV83F-015-000117 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift compression | CM-BAV83F-015-000118 | NO | NO |  | 0% |  | 0% | 0%
13 | BVF4 | Ballon de Torche | CM-ASO 83H-015-000012 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit gas lift | CM-ASO 83H-015-000009 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et drains | CM-ASO 83H-015-000011 | NO | NO |  | 0% |  | 0% | 0%
|  | Gare de racleurs | CM-ASO 83H-015-000007 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument | CM-ASO 83H-015-000014 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | CM-ASO 83H-015-000010 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-ASO 83H-015-000006 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile (typique) | CM-ASO 83H-015-000005 | NO | NO |  | 0% |  | 0% | 0%
|  | Reseau incendie | CM-ASO 83H-015-000004 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-ASO 83H-015-000008 | NO | NO |  | 0% |  | 0% | 0%
14 | ACF1 | Puits de production huile (typique) | P260-07-GE205X-PID-8510 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits d'injection d'eau (typique) | P260-07-GE205X-PID-8511 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-8514 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-07-GE205X-PID-8515 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-07-GE205X-PID-8517 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-07-GE205X-PID-8516 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon de Torche | P260-07-GE205X-PID-8560 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-8563 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-07-GE205X-PID-8562 | NO | NO |  | 0% |  | 0% | 0%
|  | Air instruments | P260-07-GE205X-PID-8565 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-07-GE205X-PID-8566 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-8513 | NO | NO |  | 0% |  | 0% | 0%
|  | Reseau incendie | P260-07-GE205X-PID-8564 | NO | NO |  | 0% |  | 0% | 0%
15 | ACF2 | Puits de production huile (typique) | P260-07-GE205X-PID-8520 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-07-GE205X-PID-8523 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-07-GE205X-PID-8524 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-07-GE205X-PID-8525 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-07-GE205X-PID-8526 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-07-GE205X-PID-8527 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon de torche | P260-07-GE205X-PID-8570 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon de torche | P260-07-GE205X-PID-8570 | NO | NO |  | 0% |  | 0% | 0%
|  | Events | P260-07-GE205X-PID-8571 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-07-GE205X-PID-8572 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz carburant | P260-07-GE205X-PID-8576 | NO | NO |  | 0% |  | 0% | 0%
|  | Air instruments | P260-07-GE205X-PID-8575 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-07-GE205X-PID-8573 | NO | NO |  | 0% |  | 0% | 0%
|  | Water injection manifold | P260-07-GE205X-PID-8519 | NO | NO |  | 0% |  | 0% | 0%
|  | Water injection manifold | P260-07-GE205X-PID-8540 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-07-GE205X-PID-8574 | NO | NO |  | 0% |  | 0% | 0%
16 | ASF2 | Instrument gas network | DISNOR-KR-ASF-02-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Multiphase export | DISNOR-KR-ASF-02-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas export | DISNOR-KR-ASF-02-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Cold vent network | DISNOR-KR-ASF-02-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production huile (typique) | P260-06-GE205X-PID-8420 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production gaz | P260-06-GE205X-PID-8421 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-06-GE205X-PID-8423 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-06-GE205X-PID-8424 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-06-GE205X-PID-8425 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-06-GE205X-PID-8426 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-06-GE205X-PID-8427 | NO | NO |  | 0% |  | 0% | 0%
|  | Ballon de torche | P260-06-GE205X-PID-8470 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains fermés | P260-06-GE205X-PID-8472 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-06-GE205X-PID-8473 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-06-GE205X-PID-8476 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection produits | P260-06-GE205X-PID-8477 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-06-GE205X-PID-8474 | NO | NO |  | 0% |  | 0% | 0%
17 | ASP1 | Air instrument | P260-04-GE205X-PID-8465 | NO | NO |  | 0% |  | 0% | 0%
|  | Oil export pumps | ASP1S2-CM-ASP-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | ASP1-DIF pig receiver | DISNOR-KR-ASP-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | ASP1-BVF3 pig launcher | DISNOR-KR-ASP-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift pig ball valve to BVF3 platform | RDRGLC-CM-ASF-AP-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Pipelines arrival | ASP1S2-CM-ASP-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | Oil export | ASP1S2-CM-ASP-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%
|  | Existing open drain network | RDRGLC-CM-ASF-AP-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | Existing cold vent network | RDRGLC-CM-ASF-AP-PER-PI-H-009 | NO | NO |  | 0% |  | 0% | 0%
|  | Existing closed drain network | RDRGLC-CM-ASF-AP-PER-PI-H-010 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | P260-04-GE205X-PID-8415 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift compression | RDRGLC-CM-ASF-AP-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | Pomperie | CM-ASP-01-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift pig ball valve to ACF1 platform | RDRGLC-CM-ASF-AP-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift pig ball valve to ENF1 platform | RDRGLC-CM-ASF-AP-PER-PI-H-014 | NO | NO |  | 0% |  | 0% | 0%
|  | New production separator | RDRGLC-CM-ASF-AP-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%
18 | DIF1 | Production DIM 7 | DISNOR-KF-DIF-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | Production well 2 | DISNOR-KR-DIF-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Production well 3 | DISNOR-KR-DIF-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Production well 4 | DISNOR-KR-DIF-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | Production and test manifold | DISNOR-KR-DIF-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | Oil export | DISNOR-KF-DIF-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%
|  | Water injection manifold | DISNOR-KR-DIF-01-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | Demulsifier injection skid | DISNOR-KR-DIF-01-PER-PI-H-011 | NO | NO |  | 0% |  | 0% | 0%
|  | Corrosion inhibitor injection skid | DISNOR-KR-DIF-01-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection d'eau | DISNOR-KR-DIF-01-PER-PI-H-018 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift manifold | DIFGLC-KR-DIF-01-PER-PI-H-009 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production | DISNOR-KF-DIF-01-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de production 2 | DIFGLC-KR-DIF-01-PER-PI-H-019 | NO | NO |  | 0% |  | 0% | 0%
|  | Flare network | DIFGLC-KR-DIF-01-PER-PI-H-021 | NO | NO |  | 0% |  | 0% | 0%
|  | Test separator | DIFGLC-KR-DIF-01-PER-PI-H-022 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument 1 | DIFGLC-KR-DIF-01-PER-PI-H-023 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift compression skid | DIFGLC-KR-DIF-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Open/Close drain | DIFGLC-KR-JUB-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Réseau air instrument | DIFGLC-KR-JUB-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Pomperie | DISNOR-KF-DIF-01-PER-PI-H-016 | NO | NO |  | 0% |  | 0% | 0%
|  | Cold vent network | DISNOR-KF-DIF-01-PER-PI-H-010 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument 2 | DIFGLC-KR-DIF-01-PER-PI-H-023 | NO | NO |  | 0% |  | 0% | 0%
19 | TIKO | Cuve de purges | CM_TKO_PER_PI_H_008 | NO | NO |  | 0% |  | 0% | 0%
|  | Test separator | TKO-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits TKM-C | TKO-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
20 | MUNJA | Alimentation FG turbine | / | NO | NO |  | 0% |  | 0% | 0%
|  | Passerelle de liaison BAP-MUNJA | / | NO | NO |  | 0% |  | 0% | 0%
|  | Reseau fuel gas | / | NO | NO |  | 0% |  | 0% | 0%
|  | Air instrum | RDRLQ-CM-GEN-BP-SOT PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Potable water system | RDRLQ-CM-GEN-BP-SOT PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Fire system | RDRLQ-CM-GEN-BP-SOT PI-G-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Sewage system | RDRLQ-CM-GEN-BP-SOT PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
21 | OAK | Manifold production | OAK-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | Arrivées et depart pipes | OAK-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | OAK-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | Vent | OAK-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits production en GL | OAK-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Test separator DS1001 | OAK-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
22 | ENF1 | Ballon et reseau torche | CM-ERN85D-015-020011 | NO | NO |  | 0% |  | 0% | 0%
|  | Circuit purges et drains | CM-ERN85D-015-020012 | NO | NO |  | 0% |  | 0% | 0%
|  | Gares de racleurs | CM-ERN85D-015-020008 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | CM-ERN85D-015-020009 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | CM-ERN85D-015-020006 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits de production (typique) | CM-ERN85D-015-020005 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | CM-ERN85D-015-020007 | NO | NO |  | 0% |  | 0% | 0%
|  | Scrubber gas | CM-ERN85D-015-020010 | NO | NO |  | 0% |  | 0% | 0%
23 | LSF1 | Drains fermés | P260-06-GE205X-PID-9562 | NO | NO |  | 0% |  | 0% | 0%
|  | Drains ouverts | P260-06-GE205X-PID-9563 | NO | NO |  | 0% |  | 0% | 0%
|  | Event | P260-06-GE205X-PID-9561 | NO | NO |  | 0% |  | 0% | 0%
|  | Export huile | P260-06-GE205X-PID-9516 | NO | NO |  | 0% |  | 0% | 0%
|  | Gas lift | P260-06-GE205X-PID-9517 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instruments | P260-06-GE205X-PID-9566 | NO | NO |  | 0% |  | 0% | 0%
|  | Incendie | P260-06-GE205X-PID-9564 | NO | NO |  | 0% |  | 0% | 0%
|  | Injection de produits | P260-06-GE205X-PID-9567 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold huile | P260-06-GE205X-PID-9513 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur de test | P260-06-GE205X-PID-9514 | NO | NO |  | 0% |  | 0% | 0%
|  | Puits production huile (typique) | P260-06-GE205X-PID-9510 | NO | NO |  | 0% |  | 0% | 0%
24 | SKM | Wells SKM | SKM-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold production | SKM-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | Manifold gas lift | SKM-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Gaz instrument | SKM-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | Cold vent DS4001 | SKM-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | Separateur test DS1001 | SKM-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | Arrivée et depart risers | SKM-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%
25 | AKF1 | Well head deck | A9705948 | NO | NO |  | 0% |  | 0% | 0%

## BAP
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP | 1 | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
|  | 2 | Dessaleurs | CM-KO-72N-015-001002 | OK | OK |  | 100% |  | 0% | 0%
|  | 3 | Ballon FWKO | CM-KO-72N-015-001003 | N/A |  |  | 0% |  | 0% | 0%
|  | 4 | Slug catcher et depart huile | CM-KO-72N-015-001004 | OK | OK |  | 100% |  | 0% | 0%
|  | 5 | Chaudières | CM-KO-72N-015-001005 | N/A |  |  | 0% |  | 0% | 0%
|  | 6 | Compression | CM-KO-72N-015-001006 | N/A |  |  | 0% |  | 0% | 0%
|  | 7 | Traitement fuel gas | CM-KO-72N-015-001007 | N/A |  |  | 0% |  | 0% | 0%
|  | 8 | Rechauffage Fuel gas | CM-KO-72N-015-001008 | N/A |  |  | 0% |  | 0% | 0%
|  | 9 | Reseau injection eau | CM-KO-72N-015-001009 | N/A |  |  | 0% |  | 0% | 0%
|  | 10 | Reseau eau | CM-KO-72N-015-001010 | OK | OK |  | 100% |  | 0% | 0%
|  | 11 | Reseau eau de mer | CM-KO-72N-015-001011 | OK | OK |  | 100% |  | 0% | 0%
|  | 12 | Traitement eau-decanteur | CM-KO-72N-015-001012 | OK | OK |  | 100% |  | 0% | 0%
|  | 13 | Traitement eau-bac tampon | CM-KO-72N-015-001013 | OK | OK |  | 100% |  | 0% | 0%
|  | 14 | Traitement eau-flottateur | CM-KO-72N-015-001014 | N/A |  |  | 0% |  | 0% | 0%
|  | 15 | PID Ecrémeur | CM-KO-72N-015-001015 | N/A |  |  | 0% |  | 0% | 0%
|  | 16 | Circuit purges | CM-KO-72N-015-001016 | N/A |  |  | 0% |  | 0% | 0%
|  | 17 | Réseau Torche | CM-KO-72N-015-001017 | N/A |  |  | 0% |  | 0% | 0%
|  | 18 | Réseau Incendie | CM-KO-72N-015-001018 | N/A |  |  | 0% |  | 0% | 0%
|  | 19 | Air service et air instrument | CM-KO-72N-015-001019 | N/A |  |  | 0% |  | 0% | 0%
|  | 20 | Diesel oil | CM-KO-72N-015-001020 | N/A |  |  | 0% |  | 0% | 0%
|  | 21 | Echangeurs | CM-KO-72N-015-001021 | OK | OK |  | 100% |  | 0% | 0%
|  | 22 | Turbo generateurs | CM-KO-72N-015-001022 | N/A |  |  | 0% |  | 0% | 0%
|  | 23 | Groupe turbo pompes | CM-KO-72N-015-001023 | N/A |  |  | 0% |  | 0% | 0%
|  | 24 | Passerelle de liaison vers KLP1 | CM-KO-72N-015-001024 | OK | OK |  | 100% |  | 0% | 0%
|  | 25 | Eau Industrielle | CM-KO-72N-015-001025 | N/A |  |  | 0% |  | 0% | 0%
|  | 26 | PID cuve de purges | CM-KO-72N-015-001026 | OK | OK |  | 100% |  | 0% | 0%
|  | 27 | CFU 3504 & 3503 | CM-KO-72N-015-001027 | OK | OK |  | 100% |  | 0% | 0%
|  | 28 | Traitement eau-Hydrocyclone ID3523 | CM-KO-72N-015-001028 | OK | OK |  | 100% |  | 0% | 0%
|  | 29 | Traitement eau-Hydrocyclones | CM-KO-72N-015-001029 | OK | OK |  | 100% |  | 0% | 0%

## KLP1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
2 | KLP1 | 1 | Arrivees huile et gaz | CM-KO-72B-015-001101 | OK | NO |  | 0% |  | 0% | 0%
|  | 2 | Circuit huile | CM-KO-72B-015-001102 | OK | NO |  | 0% |  | 0% | 0%
|  | 3 | Ballon FWKO | CM-KO-72B-015-001103 | OK | NO |  | 0% |  | 0% | 0%
|  | 4 | Ballon de Torche | CM-KO-72B-015-001104 | N/A | NO |  | 0% |  | 0% | 0%
|  | 5 | Torche et events | CM-KO-72B-015-001105 | N/A | NO |  | 0% |  | 0% | 0%
|  | 6 | Pomperie | CM-KO-72B-015-001106 | N/A | NO |  | 0% |  | 0% | 0%
|  | 7 | Scrubber gas | CM-KO-72B-015-001107 | OK | NO |  | 0% |  | 0% | 0%
|  | 8 | Circuit purges | CM-KO-72B-015-001108 | N/A | NO |  | 0% |  | 0% | 0%
|  | 9 | Circuit gaz | CM-KO-72B-015-001109 | OK | NO |  | 0% |  | 0% | 0%
|  | 10 | Decanteur | CM-KO-72B-015-001110 | N/A | NO |  | 0% |  | 0% | 0%
|  | 11 | Reseau incendie | CM-KO-72B-015-001111 | OK | NO |  | 0% |  | 0% | 0%
|  | 12 | Reseau air instrumentation | CM-KO-72B-015-001112 | N/A | NO |  | 0% |  | 0% | 0%
|  | 13 | Refroidisseurs | CM-KO-72B-015-001113 | N/A | NO |  | 0% |  | 0% | 0%
|  | 14 | Passerelle de liaison vers BAP | CM-KO-72B-015-001114 | N/A | NO |  | 0% |  | 0% | 0%
|  | 15 | PID POMPES KOLEXP | CM-KO-72B-015-XXXXXX | OK | NO |  | 0% |  | 0% | 0%
|  | 16 | Passerelle de liaison vers KLF1 | CM-KO-72B-015-001115 | OK | NO |  | 0% |  | 0% | 0%

## KLF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
3 | KLF1 | 1 | Puits de production huile (typique) | CM-KO-72D-015-001201 | N/A | NO |  | 0% |  | 0% | 0%
|  | 2 | Manifold huile | CM-KO-72D-015-001202 | N/A | NO |  | 0% |  | 0% | 0%
|  | 3 | Separateur de test | CM-KO-72D-015-001203 | N/A | NO |  | 0% |  | 0% | 0%
|  | 4 | Arrivees huile et gaz | CM-KO-72D-015-001204 | OK | NO |  | 0% |  | 0% | 0%
|  | 5 | Puits d'injection et de production gaz | CM-KO-72D-015-001205 | N/A | NO |  | 0% |  | 0% | 0%
|  | 6 | Manifold gaz | CM-KO-72D-015-001206 | OK | NO |  | 0% |  | 0% | 0%
|  | 7 | Injection eau (Typique) | CM-KO-72D-015-001207 | OK | NO |  | 0% |  | 0% | 0%
|  | 8 | Production eau | CM-KO-72D-015-001208 | N/A | NO |  | 0% |  | 0% | 0%
|  | 9 | Reseau Incendie | CM-KO-72D-015-001209 | N/A | NO |  | 0% |  | 0% | 0%
|  | 10 | Circuit purges | CM-KO-72D-015-001210 | N/A | NO |  | 0% |  | 0% | 0%
|  | 11 | Reseau air instrumentation | CM-KO-72D-015-001211 | N/A | NO |  | 0% |  | 0% | 0%
|  | 12 | Passerelle de liaison vers KLP1 | CM-KO-72D-015-001212 | N/A | NO |  | 0% |  | 0% | 0%
|  | 13 | Stockage demulsifiant | CM-KO-72D-015-001213 | N/A | NO |  | 0% |  | 0% | 0%

## KLF2
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
4 | KLF2 | 1 | Drains fermés | P260-04-GE205X-PID-7272 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Export huile | P260-04-GE205X-PID-7226 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Gas lift | P260-04-GE205X-PID-7227 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Gaz instruments | P260-04-GE205X-PID-7276 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Incendie | P260-04-GE205X-PID-7274 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Manifold huile | P260-04-GE205X-PID-7223 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Puits de production huile | P260-04-GE205X-PID-7220 | NO | NO |  | 0% |  | 0% | 0%

## KLF3
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
5 | KLF3 | 1 | Air instrument | P260-07-GE205X-PID-7285 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Drains fermés | P260-07-GE205X-PID-7282 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Drains ouverts | P260-07-GE205X-PID-7283 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Event | P260-07-GE205X-PID-7281 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gas lift | P260-07-GE205X-PID-7237 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gaz instruments | P260-07-GE205X-PID-7286 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Incendie | P260-07-GE205X-PID-7284 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Manifold huile | P260-07-GE205X-PID-7233 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Puits de production huile | P260-07-GE205X-PID-7230 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Separateur de test | P260-07-GE205X-PID-7234 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Torche | P260-07-GE205X-PID-7280 | NO | NO |  | 0% |  | 0% | 0%

## KLF4
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
6 | KLF4 | 1 | Drains fermes et ballon d'event | P260-07-GE205X-PID-7292 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Drains ouverts | P260-07-GE205X-PID-7293 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Eau d'injection | P260-07-GE205X-PID-7248 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Events | P260-07-GE205X-PID-7291 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Export huile | P260-07-GE205X-PID-7246 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gas lift | P260-07-GE205X-PID-7247 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Gaz instruments | P260-07-GE205X-PID-7296 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Incendie | P260-07-GE205X-PID-7294 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Injection de produits | P260-07-GE205X-PID-7297 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Manifold huile | P260-07-GE205X-PID-7243 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Puits de production huile | P260-07-GE205X-PID-7240 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Puits de production huile 2 | P260-07-GE205X-PID-7240 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Separateur de test | P260-07-GE205X-PID-7244 | NO | NO |  | 0% |  | 0% | 0%

## NNF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
7 | NNF1 | 1 | Export huile | P260-07-GE205X-PID-8916 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Gaz lift | P260-07-GE205X-PID-8917 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Injection d'eau | P260-07-GE205X-PID-8918 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Manifold huile | P260-07-GE205X-PID-8913 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Puits production gaz | P260-07-GE205X-PID-8910 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Puits de production huile | P260-07-GE205X-PID-8912 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Puits d'injection d'eau | P260-07-GE205X-PID-8911 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Separateur de production 2 | P260-07-GE205X-PID-8915 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Separateur de production | P260-07-GE205X-PID-8915 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Separateur de test | P260-07-GE205X-PID-8914 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Torche | P260-07-GE205X-PID-8960 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Event | P260-07-GE205X-PID-8961 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Drains fermés | P260-07-GE205X-PID-8962 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Drains ouverts | P260-07-GE205X-PID-8963 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Incendie | P260-07-GE205X-PID-8964 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gaz instruments et air instruments | P260-07-GE205X-PID-8966 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Ballon er compresseur ARIEL | P260-07-GE205X-PID-8967 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Compresseur et ballon d'air | P260-07-GE205X-PID-8968 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Ballon gas lift | P260-07-GE205X-PID-8969 | NO | NO |  | 0% |  | 0% | 0%

## ITF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
8 | ITF1 | 1 | Air instrument 2 | P260-07-GE205X-PID-9265 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Air instrument | P260-07-GE205X-PID-9265 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Drains fermés | P260-07-GE205X-PID-9262 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Drains ouverts | P260-07-GE205X-PID-9263 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Event | P260-07-GE205X-PID-9261 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Export huile | P260-07-GE205X-PID-9216 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Gas lift | P260-07-GE205X-PID-9217 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Incendie | P260-07-GE205X-PID-9264 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Injection de produits | P260-07-GE205X-PID-9267 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Injection d'eau | P260-07-GE205X-PID-9218 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Manifold huile | P260-07-GE205X-PID-9213 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Manifold huile 2 | P260-07-GE205X-PID-9213 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Puits production gaz | P260-07-GE205X-PID-9211 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Puits production d'huile | P260-07-GE205X-PID-9210 | NO | NO |  | 0% |  | 0%
|  | 15 | Puits injection d'eau | P260-07-GE205X-PID-9212 | NO | NO |  | 0% |  | 0%
|  | 16 | Separateur de test | P260-07-GE205X-PID-9214 | NO | NO |  | 0% |  | 0%
|  | 17 | Separateur de production | P260-07-GE205X-PID-9215 | NO | NO |  | 0% |  | 0%
|  | 18 | Torche | P260-07-GE205X-PID-9260 | NO | NO |  | 0% |  | 0%
|  | 19 | Ballon et compresseur Ariel | P260-07-GE205X-PID-9268 | NO | NO |  | 0% |  | 0%

## DKF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
9 | DKF1 | 1 | Puits de production d'huile | CM-KOL72S-015-001005 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Expedition huile | CM-KOL72S-015-001006 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Manifold huile | CM-KOL72S-015-001007 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Appareil de test | CM-KOL72S-015-001008 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Circuit gas lift | CM-KOL72S-015-001009 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Circuit purges et gaz | CM-KOL72S-015-001010 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Gaz instruments | CM-KOL72S-015-001011 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Separateur DS1002 | CM-KOL72S-015-001012 | NO | NO |  | 0% |  | 0% | 0%

## BVF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
10 | BVF1 | 1 | Ballon de Torche | CM-BVM83B-015-000015 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Circuit gas lift | CM-BVM83B-015-000012 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Circuit purges et drains | CM-BVM83B-015-000014 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Gare de racleurs huile/gaz | CM-BVM83B-015-000007 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gaz instrument | CM-BVM83B-015-000017 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Injection d'eau | CM-BVM83B-015-000018 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Manifold gas lift | CM-BVM83B-015-000013 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Manifold huile | CM-BVM83B-015-000006 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Pomperie | CM-BVM83B-015-000008 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Puits de production huile (typique) | CM-BVM83B-015-000005 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Reseau incendie | CM-BVM83B-015-000016 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Separateur 1er etage | CM-BVM83B-015-000010 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Separateur 2ème etage | CM-BVM83B-015-000011 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Separateur de test | CM-BVM83B-015-000009 | NO | NO |  | 0% |  | 0% | 0%

## BVF2
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
11 | BVF2 | 1 | Ballon de Torche | CM-ASO83D-015-001015 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Scrubber gas lift | CM-ASO83D-015-001012 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Circuit purges et drains | CM-ASO83D-015-001014 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Gare de racleurs | CM-ASO83D-015-001007 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gaz instrument | CM-ASO83D-015-001016 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Manifold gas lift | CM-ASO83D-015-001013 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Manifold huile | CM-ASO83D-015-001006 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Pomperie | CM-ASO83D-015-001008 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Puits de production huile (typique) | CM-ASO83D-015-001005 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Separateur 1er etage | CM-ASO83D-015-001010 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Separateur 2ème etage | CM-ASO83D-015-001011 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Separateur de test | CM-ASO83D-015-001009 | NO | NO |  | 0% |  | 0% | 0%

## BVF3
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
12 | BVF3 | 1 | Puits de production huile (typique) | CM-BAV83F-015-000105 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Manifold huile | CM-BAV83F-015-000106 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Gare de racleurs | CM-BAV83F-015-000107 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Pomperie | CM-BAV83F-015-000108 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Separateur de test | CM-BAV83F-015-000109 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Separateur 1er etage | CM-BAV83F-015-000110 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Separateur 2ème etage | CM-BAV83F-015-000111 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Manifold gas lift | CM-BAV83F-015-000112 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Circuit gas lift | CM-BAV83F-015-000113 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Circuit purges et drains | CM-BAV83F-015-000114 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Ballon de Torche | CM-BAV83F-015-000115 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Injection d'eau et réseau incendie | CM-BAV83F-015-000116 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Gaz instrument | CM-BAV83F-015-000117 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Gas lift compression | CM-BAV83F-015-000118 | NO | NO |  | 0% |  | 0% | 0%

## BVF4
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
12 | BVF4 | 1 | Ballon de Torche | CM-ASO 83H-015-000012 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Circuit gas lift | CM-ASO 83H-015-000009 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Circuit purges et drains | CM-ASO 83H-015-000011 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Gare de racleurs | CM-ASO 83H-015-000007 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gaz instrument | CM-ASO 83H-015-000014 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Manifold gas lift | CM-ASO 83H-015-000010 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Manifold huile | CM-ASO 83H-015-000006 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Puits de production huile (typique) | CM-ASO 83H-015-000005 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Reseau incendie | CM-ASO 83H-015-000004 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Separateur de test | CM-ASO 83H-015-000008 | NO | NO |  | 0% |  | 0% | 0%

## ACF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
13 | ACF1 | 1 | Puits de production huile (typique) | P260-07-GE205X-PID-8510 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Puits d'injection d'eau (typique) | P260-07-GE205X-PID-8511 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Separateur de test | P260-07-GE205X-PID-8514 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Separateur de production | P260-07-GE205X-PID-8515 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gas lift | P260-07-GE205X-PID-8517 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Export huile | P260-07-GE205X-PID-8516 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Ballon de Torche | P260-07-GE205X-PID-8560 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Drains ouverts | P260-07-GE205X-PID-8563 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Drains fermés | P260-07-GE205X-PID-8562 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Air instruments | P260-07-GE205X-PID-8565 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gaz instruments | P260-07-GE205X-PID-8566 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Manifold huile | P260-07-GE205X-PID-8513 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Reseau incendie | P260-07-GE205X-PID-8564 | NO | NO |  | 0% |  | 0% | 0%

## ACF2
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
14 | ACF2 | 1 | Puits de production huile (typique) | P260-07-GE205X-PID-8520 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Manifold huile | P260-07-GE205X-PID-8523 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Separateur de test | P260-07-GE205X-PID-8524 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Separateur de production | P260-07-GE205X-PID-8525 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Export huile | P260-07-GE205X-PID-8526 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gas lift | P260-07-GE205X-PID-8527 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Ballon de torche | P260-07-GE205X-PID-8570 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Ballon de torche | P260-07-GE205X-PID-8570 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Events | P260-07-GE205X-PID-8571 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Drains fermés | P260-07-GE205X-PID-8572 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gaz carburant | P260-07-GE205X-PID-8576 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Air instruments | P260-07-GE205X-PID-8575 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Drains ouverts | P260-07-GE205X-PID-8573 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Water injection manifold | P260-07-GE205X-PID-8519 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Water injection manifold | P260-07-GE205X-PID-8540 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Incendie | P260-07-GE205X-PID-8574 | NO | NO |  | 0% |  | 0% | 0%

## ASF2
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
15 | ASF2 | 1 | Instrument gas network | DISNOR-KR-ASF-02-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Multiphase export | DISNOR-KR-ASF-02-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Gas export | DISNOR-KR-ASF-02-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Cold vent network | DISNOR-KR-ASF-02-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Puits de production huile (typique) | P260-06-GE205X-PID-8420 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Puits de production gaz | P260-06-GE205X-PID-8421 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Manifold huile | P260-06-GE205X-PID-8423 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Separateur de test | P260-06-GE205X-PID-8424 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Separateur de production | P260-06-GE205X-PID-8425 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Export huile | P260-06-GE205X-PID-8426 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gas lift | P260-06-GE205X-PID-8427 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Ballon de torche | P260-06-GE205X-PID-8470 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Drains fermés | P260-06-GE205X-PID-8472 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Drains ouverts | P260-06-GE205X-PID-8473 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Gaz instruments | P260-06-GE205X-PID-8476 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Injection produits | P260-06-GE205X-PID-8477 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Incendie | P260-06-GE205X-PID-8474 | NO | NO |  | 0% |  | 0% | 0%

## ASP1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
16 | ASP1 | 1 | Air instrument | P260-04-GE205X-PID-8465 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Oil export pumps | ASP1S2-CM-ASP-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | ASP1-DIF pig receiver | DISNOR-KR-ASP-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | ASP1-BVF3 pig launcher | DISNOR-KR-ASP-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gas lift pig ball valve to BVF3 platform | RDRGLC-CM-ASF-AP-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Pipelines arrival | ASP1S2-CM-ASP-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Oil export | ASP1S2-CM-ASP-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Existing open drain network | RDRGLC-CM-ASF-AP-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Existing cold vent network | RDRGLC-CM-ASF-AP-PER-PI-H-009 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Existing closed drain network | RDRGLC-CM-ASF-AP-PER-PI-H-010 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Separateur de production | P260-04-GE205X-PID-8415 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Gas lift compression | RDRGLC-CM-ASF-AP-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Pomperie | CM-ASP-01-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Gas lift pig ball valve to ACF1 platform | RDRGLC-CM-ASF-AP-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Gas lift pig ball valve to ENF1 platform | RDRGLC-CM-ASF-AP-PER-PI-H-014 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | New production separator | RDRGLC-CM-ASF-AP-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%

## DIF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
17 | DIF1 | 1 | Production DIM 7 | DISNOR-KF-DIF-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Production well 2 | DISNOR-KR-DIF-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Production well 3 | DISNOR-KR-DIF-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Production well 4 | DISNOR-KR-DIF-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Production and test manifold | DISNOR-KR-DIF-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Oil export | DISNOR-KF-DIF-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Water injection manifold | DISNOR-KR-DIF-01-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Demulsifier injection skid | DISNOR-KR-DIF-01-PER-PI-H-011 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Corrosion inhibitor injection skid | DISNOR-KR-DIF-01-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Injection d'eau | DISNOR-KR-DIF-01-PER-PI-H-018 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gas lift manifold | DIFGLC-KR-DIF-01-PER-PI-H-009 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Separateur de production | DISNOR-KF-DIF-01-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Separateur de production 2 | DIFGLC-KR-DIF-01-PER-PI-H-019 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Flare network | DIFGLC-KR-DIF-01-PER-PI-H-021 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Test separator | DIFGLC-KR-DIF-01-PER-PI-H-022 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gaz instrument 1 | DIFGLC-KR-DIF-01-PER-PI-H-023 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Gas lift compression skid | DIFGLC-KR-DIF-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Open/Close drain | DIFGLC-KR-JUB-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Réseau air instrument | DIFGLC-KR-JUB-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Pomperie | DISNOR-KF-DIF-01-PER-PI-H-016 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Cold vent network | DISNOR-KF-DIF-01-PER-PI-H-010 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Gaz instrument 2 | DIFGLC-KR-DIF-01-PER-PI-H-023 | NO | NO |  | 0% |  | 0% | 0%

## TIKO
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
18 | TIKO | 1 | Cuve de purges | CM_TKO_PER_PI_H_008 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Test separator | TKO-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Puits TKM-C | TKO-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%

## MUNJA
PID CENSUS
Plateform N° | Plateforms | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[6 empty] | 100% |  | 100% | 100%
1 | BAP | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
19 | MUNJA | Alimentation FG turbine | / | NO | NO |  | 0% |  | 0% | 0%
|  | Passerelle de liaison BAP-MUNJA | / | NO | NO |  | 0% |  | 0% | 0%
|  | Reseau fuel gas | / | NO | NO |  | 0% |  | 0% | 0%
|  | Air instrum | RDRLQ-CM-GEN-BP-SOT PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Potable water system | RDRLQ-CM-GEN-BP-SOT PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | Fire system | RDRLQ-CM-GEN-BP-SOT PI-G-001 | NO | NO |  | 0% |  | 0% | 0%
|  | Sewage system | RDRLQ-CM-GEN-BP-SOT PI-H-005 | NO | NO |  | 0% |  | 0% | 0%

## OAK
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
20 | OAK | 1 | Manifold production | OAK-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Arrivées et depart pipes | OAK-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Gaz instruments | OAK-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Vent | OAK-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Puits production en GL | OAK-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Test separator DS1001 | OAK-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%

## ENF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
21 | ENF1 | 1 | Ballon et reseau torche | CM-ERN85D-015-020011 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Circuit purges et drains | CM-ERN85D-015-020012 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Gares de racleurs | CM-ERN85D-015-020008 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Manifold gas lift | CM-ERN85D-015-020009 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Manifold huile | CM-ERN85D-015-020006 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Puits de production (typique) | CM-ERN85D-015-020005 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Separateur de test | CM-ERN85D-015-020007 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Scrubber gas | CM-ERN85D-015-020010 | NO | NO |  | 0% |  | 0% | 0%

## LSF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
22 | LSF1 | 1 | Drains fermés | P260-06-GE205X-PID-9562 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Drains ouverts | P260-06-GE205X-PID-9563 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Event | P260-06-GE205X-PID-9561 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Export huile | P260-06-GE205X-PID-9516 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Gas lift | P260-06-GE205X-PID-9517 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gaz instruments | P260-06-GE205X-PID-9566 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Incendie | P260-06-GE205X-PID-9564 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Injection de produits | P260-06-GE205X-PID-9567 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Manifold huile | P260-06-GE205X-PID-9513 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Separateur de test | P260-06-GE205X-PID-9514 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Puits production huile (typique) | P260-06-GE205X-PID-9510 | NO | NO |  | 0% |  | 0% | 0%

## SKM
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
1 | BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
23 | SKM | 1 | Wells SKM | SKM-01-PER-PI-H-001 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Manifold production | SKM-01-PER-PI-H-002 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Manifold gas lift | SKM-01-PER-PI-H-003 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Gaz instrument | SKM-01-PER-PI-H-004 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Cold vent DS4001 | SKM-01-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Separateur test DS1001 | SKM-01-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Arrivée et depart risers | SKM-01-PER-PI-H-007 | NO | NO |  | 0% |  | 0% | 0%

## AKF1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% |  | 100% | 100%
| BAP |  | Arrivées huile | CM-KO-72N-015-001001 | OK | OK |  | 100% |  | 0% | 0%
25 | AKF1 | 1 | Well head deck | A9705948 | NO | NO |  | 0% |  | 0% | 0%