## Feuil2 (hidden)
ESF1 | BAP | COMPLEXE
BJF1 | KLP1 | SUD
BKF1 | KLF1 | NORD
BOF1 | KLF2
BOF2 | KLF3 | COMPLEXE | BAF 3
BRF1 | KLF4 | CENTRE | BAF T1
BTF1 | NNF1 | NORD | BAF T2
BTF2 | ITF1 |  | KB 4-5
EKF1 | DKF1 |  | KB GAS
EKF2 | DKF2 |  | KB NORD
EKF3 | SIRONA |  | KL
ESP 2 | BVF1 |  | EBOME
ESP1 | BVF2 |  | KF7
INF1 | BVF3 |  | KF8
KCF1 | BVF4 |  | KF9
KCF2 | AKF1
KCF3 | ACF1
KEF1 | ACF2
KNF1 | ASP1
VT | ASP2
DIF1
DIF2
OAK
ENF1
LSF1

## SOUTH
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% | 100% | 100% | 100% | 100%
1 | BIPAGA | 1 | 12'' production line pig receiver A | FLNG-CM-SAS-BA-PER-PI-H-100 | NO | NO |  | 0% | 100% | 0% | 0%
|  | 2 | 12'' production line pig receiver B | FLNG-CM-SAS-BA-PER-PI-H-101 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Slug catcher | FLNG-CM-SAS-BA-PER-PI-H-110 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Liquid flash drum | FLNG-CM-SAS-BA-PER-PI-H-112 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Existing condensate flash drum | FLNG-CM-SAS-BA-PER-PI-H-114 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Existing condensate flash drum (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-115 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Lt gas/condensate exchanger | FLNG-CM-SAS-BA-PER-PI-H-130 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Gas heat exchangers | FLNG-CM-SAS-BA-PER-PI-H-131 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | LT sunction scrubber | FLNG-CM-SAS-BA-PER-PI-H-133 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Turbo expander train A | FLNG-CM-SAS-BA-PER-PI-H-134 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Turbo expander-compressor interfaces | FLNG-CM-SAS-BA-PER-PI-H-135 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Turbo expander train B | FLNG-CM-SAS-BA-PER-PI-H-136 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Low temperature separator | FLNG-CM-SAS-BA-PER-PI-H-138 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Gas export sunction scrubber | FLNG-CM-SAS-BA-PER-PI-H-139 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Gas export turbo compressor train A | FLNG-CM-SAS-BA-PER-PI-H-141 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gas export air cooler train A | FLNG-CM-SAS-BA-PER-PI-H-142 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Gas export turbo compressor train B | FLNG-CM-SAS-BA-PER-PI-H-144 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Gas export air cooler train B | FLNG-CM-SAS-BA-PER-PI-H-145 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Gas export turbo compressor train C | FLNG-CM-SAS-BA-PER-PI-H-147 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Gas export air cooler train C | FLNG-CM-SAS-BA-PER-PI-H-148 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Main power generator A | FLNG-CM-SAS-BA-PER-PI-H-200 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Existing pig receiver | FLNG-CM-SAS-BA-PER-PI-H-201 | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Existing gas metering package skid UN-221-A/B | FLNG-CM-SAS-BA-PER-PI-H-203 | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Emergency power generator | FLNG-CM-SAS-BA-PER-PI-H-204 | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Export gas metering | FLNG-CM-SAS-BA-PER-PI-H-220 | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Existing pressure reducing & filtering station | FLNG-CM-SAS-BA-PER-PI-H-250 | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Existing pressure reducing & filtering station (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-251 | NO | NO |  | 0% |  | 0% | 0%
|  | 28 | De-ethanizer pre-heater | FLNG-CM-SAS-BA-PER-PI-H-291 | NO | NO |  | 0% |  | 0% | 0%
|  | 29 | De-ethanizer column | FLNG-CM-SAS-BA-PER-PI-H-292 | NO | NO |  | 0% |  | 0% | 0%
|  | 30 | De-ethanizer reboiler | FLNG-CM-SAS-BA-PER-PI-H-293 | NO | NO |  | 0% |  | 0% | 0%
|  | 31 | De-ethanizer condenser & reflux drum | FLNG-CM-SAS-BA-PER-PI-H-294 | NO | NO |  | 0% |  | 0% | 0%
|  | 32 | De-ethanizer reflux pumps | FLNG-CM-SAS-BA-PER-PI-H-295 | NO | NO |  | 0% |  | 0% | 0%
|  | 33 | Propane compressor | FLNG-CM-SAS-BA-PER-PI-H-296 | NO | NO |  | 0% |  | 0% | 0%
|  | 34 | Stabiliser column | FLNG-CM-SAS-BA-PER-PI-H-300 | NO | NO |  | 0% |  | 0% | 0%
|  | 35 | Stabiliser reboiler | FLNG-CM-SAS-BA-PER-PI-H-301 | NO | NO |  | 0% |  | 0% | 0%
|  | 36 | Stabiliser condenser & reflux drum | FLNG-CM-SAS-BA-PER-PI-H-302 | NO | NO |  | 0% |  | 0% | 0%
|  | 37 | Stabiliser reflux pumps | FLNG-CM-SAS-BA-PER-PI-H-303 | NO | NO |  | 0% |  | 0% | 0%
|  | 38 | LPG pumps & metering | FLNG-CM-SAS-BA-PER-PI-H-304 | NO | NO |  | 0% |  | 0% | 0%
|  | 39 | Existing pig receiver liquid | FLNG-CM-SAS-BA-PER-PI-H-305 | NO | NO |  | 0% |  | 0% | 0%
|  | 40 | Existing condensate surge drum | FLNG-CM-SAS-BA-PER-PI-H-306 | NO | NO |  | 0% |  | 0% | 0%
|  | 41 | Existing condensate heater | FLNG-CM-SAS-BA-PER-PI-H-308 | NO | NO |  | 0% |  | 0% | 0%
|  | 42 | Existing condensate heater (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-309 | NO | NO |  | 0% |  | 0% | 0%
|  | 43 | Existing condensate storage tank | FLNG-CM-SAS-BA-PER-PI-H-400 | NO | NO |  | 0% |  | 0% | 0%
|  | 44 | Existing condensate storage tank (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-401 | NO | NO |  | 0% |  | 0% | 0%
|  | 45 | Condensate storage tank | FLNG-CM-SAS-BA-PER-PI-H-403 | NO | NO |  | 0% |  | 0% | 0%
|  | 46 | Existing storage export pumps | FLNG-CM-SAS-BA-PER-PI-H-405 | NO | NO |  | 0% |  | 0% | 0%
|  | 47 | Existing condensate export pumps (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-406 | NO | NO |  | 0% |  | 0% | 0%
|  | 48 | Condensate export pumps | FLNG-CM-SAS-BA-PER-PI-H-407 | NO | NO |  | 0% |  | 0% | 0%
|  | 49 | Existing condensate pig launcher | FLNG-CM-SAS-BA-PER-PI-H-408 | NO | NO |  | 0% |  | 0% | 0%
|  | 50 | Existing MVIA oil reception | FLNG-CM-SAS-BA-PER-PI-H-409 | NO | NO |  | 0% |  | 0% | 0%
|  | 51 | Produced water degasser | FLNG-CM-SAS-BA-PER-PI-H-450 | NO | NO |  | 0% |  | 0% | 0%
|  | 52 | Fuel gas scrubber | FLNG-CM-SAS-BA-PER-PI-H-500 | NO | NO |  | 0% |  | 0% | 0%
|  | 53 | Fuel gas heater, filter and distribution network | FLNG-CM-SAS-BA-PER-PI-H-501 | NO | NO |  | 0% |  | 0% | 0%
|  | 54 | Existing HP-LP fuel gas headers | FLNG-CM-SAS-BA-PER-PI-H-502 | NO | NO |  | 0% |  | 0% | 0%
|  | 55 | Existing HP-LP fuel gas headers (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-503 | NO | NO |  | 0% |  | 0% | 0%
|  | 56 | Existing fuel gas unit | FLNG-CM-SAS-BA-PER-PI-H-504 | NO | NO |  | 0% |  | 0% | 0%
|  | 57 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-505 | NO | NO |  | 0% |  | 0% | 0%
|  | 58 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-506 | NO | NO |  | 0% |  | 0% | 0%
|  | 59 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-507 | NO | NO |  | 0% |  | 0% | 0%
|  | 60 | Existing fire water storage tank | FLNG-CM-SAS-BA-PER-PI-H-601 | NO | NO |  | 0% |  | 0% | 0%
|  | 61 | Fire water network | FLNG-CM-SAS-BA-PER-PI-H-604 | NO | NO |  | 0% |  | 0% | 0%
|  | 62 | Fire water network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-605 | NO | NO |  | 0% |  | 0% | 0%
|  | 63 | Fire water pumps | FLNG-CM-SAS-BA-PER-PI-H-606 | NO | NO |  | 0% |  | 0% | 0%
|  | 64 | MEG regeneration package | FLNG-CM-SAS-BA-PER-PI-H-700 | NO | NO |  | 0% |  | 0% | 0%
|  | 65 | Existing meg storage tank | FLNG-CM-SAS-BA-PER-PI-H-701 | NO | NO |  | 0% |  | 0% | 0%
|  | 66 | Existing MEG pumps | FLNG-CM-SAS-BA-PER-PI-H-702 | NO | NO |  | 0% |  | 0% | 0%
|  | 67 | Existing Meg regeneration package | FLNG-CM-SAS-BA-PER-PI-H-711 | NO | NO |  | 0% |  | 0% | 0%
|  | 68 | Air compressor, air receiver,nitrogen genration package | FLNG-CM-SAS-BA-PER-PI-H-820 | NO | NO |  | 0% |  | 0% | 0%
|  | 69 | Instrument air distribution | FLNG-CM-SAS-BA-PER-PI-H-821 | NO | NO |  | 0% |  | 0% | 0%
|  | 70 | Existing instrument air network | FLNG-CM-SAS-BA-PER-PI-H-822 | NO | NO |  | 0% |  | 0% | 0%
|  | 71 | Existing air instrument/nitrogen production | FLNG-CM-SAS-BA-PER-PI-H-823 | NO | NO |  | 0% |  | 0% | 0%
|  | 72 | Existing instrument air network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-824 | NO | NO |  | 0% |  | 0% | 0%
|  | 73 | Nitrogen generation packages and nitrogen receiver (cancelled) | FLNG-CM-SAS-BA-PER-PI-H-830 | NO | NO |  | 0% |  | 0% | 0%
|  | 74 | Existing and new nitrogen network | FLNG-CM-SAS-BA-PER-PI-H-832 | NO | NO |  | 0% |  | 0% | 0%
|  | 75 | Existing nitrogen network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-834 | NO | NO |  | 0% |  | 0% | 0%
|  | 76 | Existing diesel oil storage and transfer | FLNG-CM-SAS-BA-PER-PI-H-840 | NO | NO |  | 0% |  | 0% | 0%
|  | 77 | Existing diesel oil storage and transfer (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-841 | NO | NO |  | 0% |  | 0% | 0%
|  | 78 | Hot oil fired heater | FLNG-CM-SAS-BA-PER-PI-H-850 | NO | NO |  | 0% |  | 0% | 0%
|  | 79 | Hot oil expansion drum and pumps | FLNG-CM-SAS-BA-PER-PI-H-853 | NO | NO |  | 0% |  | 0% | 0%
|  | 80 | Hot oil filling system | FLNG-CM-SAS-BA-PER-PI-H-854 | NO | NO |  | 0% |  | 0% | 0%
|  | 81 | Chilling wtaer system A | FLNG-CM-SAS-BA-PER-PI-H-870 | NO | NO |  | 0% |  | 0% | 0%
|  | 82 | Chilling wtaer system B | FLNG-CM-SAS-BA-PER-PI-H-871 | NO | NO |  | 0% |  | 0% | 0%
|  | 83 | Cooling water pumps and expansion drum | FLNG-CM-SAS-BA-PER-PI-H-872 | NO | NO |  | 0% |  | 0% | 0%
|  | 84 | Corrosion inhibitor injection system | FLNG-CM-SAS-BA-PER-PI-H-891 | NO | NO |  | 0% |  | 0% | 0%
|  | 85 | HP & LP flare headers | FLNG-CM-SAS-BA-PER-PI-H-910 | NO | NO |  | 0% |  | 0% | 0%
|  | 86 | Existing LP flare header (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-912 | NO | NO |  | 0% |  | 0% | 0%
|  | 87 | Existing flare system | FLNG-CM-SAS-BA-PER-PI-H-913 | NO | NO |  | 0% |  | 0% | 0%
|  | 88 | HP flare KO drum, pumps and tip | FLNG-CM-SAS-BA-PER-PI-H-914 | NO | NO |  | 0% |  | 0% | 0%
|  | 89 | Existing LP flare header | FLNG-CM-SAS-BA-PER-PI-H-916 | NO | NO |  | 0% |  | 0% | 0%
|  | 90 | Existing LP flare header (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-917 | NO | NO |  | 0% |  | 0% | 0%
|  | 91 | Vent header and Tip (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-918 | NO | NO |  | 0% |  | 0% | 0%
|  | 92 | Vent header and Tip | FLNG-CM-SAS-BA-PER-PI-H-920 | NO | NO |  | 0% |  | 0% | 0%
|  | 93 | Open drain headers (cancelled) | FLNG-CM-SAS-BA-PER-PI-H-930 | NO | NO |  | 0% |  | 0% | 0%
|  | 94 | Existing open drain system | FLNG-CM-SAS-BA-PER-PI-H-932 | NO | NO |  | 0% |  | 0% | 0%
|  | 95 | Existing open drain system (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-933 | NO | NO |  | 0% |  | 0% | 0%
|  | 96 | Existing closed drain headers | FLNG-CM-SAS-BA-PER-PI-H-991 | NO | NO |  | 0% |  | 0% | 0%
|  | 97 | Existing closed drain headers (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-992 | NO | NO |  | 0% |  | 0% | 0%
|  | 98 | Closed drain headers | FLNG-CM-SAS-BA-PER-PI-H-993 | NO | NO |  | 0% |  | 0% | 0%
|  | 99 | Existing closed drain & flare KO drum | FLNG-CM-SAS-BA-PER-PI-H-994 | NO | NO |  | 0% |  | 0% | 0%
|  | 100 | Existing closed drain & flare KO drum (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-995 | NO | NO |  | 0% |  | 0% | 0%
2 | EBOME | 1 | Puits EBOME | KCEBD004-CM-EP-PER-H017 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Monopodes | EBM 004 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Separateur 1er etage V101 A | KCEBD004-CM-EP-PER-H001 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Separateur 1er etage V101 B | KCEBD004-CM-EP-PER-H002 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Separateur 1er etage V101 C | KCEBD004-CM-EP-PER-H003 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Separateur 1er etage V101 D | KCEBD004-CM-EP-PER-H004 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Separateur 2ème etage | KCEBD004-CM-EP-PER-H005 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Scrubber gaz | KCEBD004-CM-EP-PER-H006 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Export huile | EBM 010 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Manifold huile | KCEBD004-CM-EP-PER-H016 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gaz lift | KCEBD004-CM-EP-PER-H007 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Torche | KCEBD004-CM-EP-PER-H008 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Traitement des eaux-SILLOS | EBM 015 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Drains | KCEBD004-CM-EP-PER-H009 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Compresseur 2 ème etage | KCEBD004-CM-EP-PER-H012 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Compresseur 1er etage | KCEBD004-CM-EP-PER-H010 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Compresseur gas lift | KCEBD004-CM-EP-PER-H013 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Manifold gaz HP/BP | KCEBD004-CM-EP-PER-H014 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Manifold decompression GL | KCEBD004-CM-EP-PER-H016 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Eau de mer | EBM 019 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Reseau incendie | EBM 020 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Injection d'eau | EBM 021 | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Bacs petrole generateurs | EBM 022 | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Eau douce | EBM 023 | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Circuit de refroidissement | EBM 024 | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Air comprime | EBM 025 | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Gazoil | EBM 026 | NO | NO
|  | 28 | Ventilation | EBM 027 | NO | NO
|  | 29 | Dessableur | EBM 031 | NO | NO |  | 0% |  | 0% | 0%
3 | SANAGA 1 | 1 | Well head 101 | FLN2-CM-SAS-S1-PER-PI-H-101 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Well head 102 | FLN2-CM-SAS-S1-PER-PI-H-102 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Well head 103 | FLN2-CM-SAS-S1-PER-PI-H-103 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Well head 104 | FLN2-CM-SAS-S1-PER-PI-H-104 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Well head 105 | FLN2-CM-SAS-S1-PER-PI-H-105 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | KB gas line pig receiver | FLN2-CM-SAS-S1-PER-PI-H-106 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Existing production manifold | FLN2-CM-SAS-S1-PER-PI-H-109 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | New production manifold | FLN2-CM-SAS-S1-PER-PI-H-110 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Free water knock out drum | FLN2-CM-SAS-S1-PER-PI-H-111 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Gas pig launcher to Bipaga | FLN2-CM-SAS-S1-PER-PI-H-112 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gas cooling - SW exchanger | FLN2-CM-SAS-S1-PER-PI-H-113 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Temporary pig launcher and receiver skid | FLN2-CM-SAS-S1-PER-PI-H-115 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Well head 106 | FLN2-CM-SAS-S1-PER-PI-H-116 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Liquid/gas heat exchanger | FLN2-CM-SAS-S1-PER-PI-H-120 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Low temperature separator | FLN2-CM-SAS-S1-PER-PI-H-121 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gas pig launcher | FLN2-CM-SAS-S1-PER-PI-H-122 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Gas heat exchanger | FLN2-CM-SAS-S1-PER-PI-H-123 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Produced water treatment | FLN2-CM-SAS-S1-PER-PI-H-130 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Manifolds for liquid export | FLN2-CM-SAS-S1-PER-PI-H-131 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Liquid export | FLN2-CM-SAS-S1-PER-PI-H-132 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Liquid export to EBOME | FLN2-CM-SAS-S1-PER-PI-H-133 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Sea water lift pumps | FLN2-CM-SAS-S1-PER-PI-H-150 | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Offshore diesel | FLN2-CM-SAS-S1-PER-PI-H-160 | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Vent & closed drain system | FLN2-CM-SAS-S1-PER-PI-H-910 | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Drain tank and drain tank pump | FLN2-CM-SAS-S1-PER-PI-H-920 | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Chemical injection skid | FLN2-CM-SAS-S1-PER-PI-H-960 | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Vent collection network | FLN2-CM-SAS-S1-PER-PI-H-970 | NO | NO |  | 0% |  | 0% | 0%
4 | SANAGA 2 | 1 | Battery limit sanaga-bridge | FLN2-CM-SAS-S1-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Gas inlet air cooler | FLN2-CM-SAS-S1-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Production separation | FLN2-CM-SAS-S1-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | LP turbocompressor sunction scrubber | FLN2-CM-SAS-S1-PER-PI-H-009-1 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | LP turbocompressor train A | FLN2-CM-SAS-S1-PER-PI-H-009-2 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gas air cooler-train A | FLN2-CM-SAS-S1-PER-PI-H-010-1 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | LP turbocompressor train B | FLN2-CM-SAS-S1-PER-PI-H-011 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Gas air cooler-train B | FLN2-CM-SAS-S1-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | LP turbocompressor train C | FLN2-CM-SAS-S1-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Gas air cooler-train C | FLN2-CM-SAS-S1-PER-PI-H-014 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Booster compressor sunction scrubber | FLN2-CM-SAS-S1-PER-PI-H-014-2 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Booster compressor for KPDC | FLN2-CM-SAS-S1-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Fuel gas scrubber D-040 | FLN2-CM-SAS-S1-PER-PI-H-020 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Fuel gas heater, filter and distribution network | FLN2-CM-SAS-S1-PER-PI-H-021 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Air compressor, air receiver,nitrogen genration package | FLN2-CM-SAS-S1-PER-PI-H-022 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Condensate export pumps | FLN2-CM-SAS-S1-PER-PI-H-025 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Produced water degasser and pumps | FLN2-CM-SAS-S1-PER-PI-H-029 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Emergency power generator | FLN2-CM-SAS-S1-PER-PI-H-090 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Main power generator TG-2002B | FLN2-CM-SAS-S1-PER-PI-H-200 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Sea water fire fighting pumps | FLN2-CM-SAS-S1-PER-PI-H-250 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Offshore diesel | FLN2-CM-SAS-S1-PER-PI-H-260 | NO | NO |  | 0% |  | 0% | 0%

## BIPAGA
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% | 100% | 100% | 100% | 100%
1 | BIPAGA | 1 | 12'' production line pig receiver A | FLNG-CM-SAS-BA-PER-PI-H-100 | NO | NO |  | 0% | 100% | 0% | 0%
|  | 2 | 12'' production line pig receiver B | FLNG-CM-SAS-BA-PER-PI-H-101 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Slug catcher | FLNG-CM-SAS-BA-PER-PI-H-110 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Liquid flash drum | FLNG-CM-SAS-BA-PER-PI-H-112 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Existing condensate flash drum | FLNG-CM-SAS-BA-PER-PI-H-114 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Existing condensate flash drum (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-115 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Lt gas/condensate exchanger | FLNG-CM-SAS-BA-PER-PI-H-130 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Gas heat exchangers | FLNG-CM-SAS-BA-PER-PI-H-131 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | LT sunction scrubber | FLNG-CM-SAS-BA-PER-PI-H-133 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Turbo expander train A | FLNG-CM-SAS-BA-PER-PI-H-134 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Turbo expander-compressor interfaces | FLNG-CM-SAS-BA-PER-PI-H-135 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Turbo expander train B | FLNG-CM-SAS-BA-PER-PI-H-136 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Low temperature separator | FLNG-CM-SAS-BA-PER-PI-H-138 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Gas export sunction scrubber | FLNG-CM-SAS-BA-PER-PI-H-139 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Gas export turbo compressor train A | FLNG-CM-SAS-BA-PER-PI-H-141 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gas export air cooler train A | FLNG-CM-SAS-BA-PER-PI-H-142 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Gas export turbo compressor train B | FLNG-CM-SAS-BA-PER-PI-H-144 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Gas export air cooler train B | FLNG-CM-SAS-BA-PER-PI-H-145 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Gas export turbo compressor train C | FLNG-CM-SAS-BA-PER-PI-H-147 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Gas export air cooler train C | FLNG-CM-SAS-BA-PER-PI-H-148 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Main power generator A | FLNG-CM-SAS-BA-PER-PI-H-200 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Existing pig receiver | FLNG-CM-SAS-BA-PER-PI-H-201 | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Existing gas metering package skid UN-221-A/B | FLNG-CM-SAS-BA-PER-PI-H-203 | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Emergency power generator | FLNG-CM-SAS-BA-PER-PI-H-204 | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Export gas metering | FLNG-CM-SAS-BA-PER-PI-H-220 | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Existing pressure reducing & filtering station | FLNG-CM-SAS-BA-PER-PI-H-250 | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Existing pressure reducing & filtering station (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-251 | NO | NO |  | 0% |  | 0% | 0%
|  | 28 | De-ethanizer pre-heater | FLNG-CM-SAS-BA-PER-PI-H-291 | NO | NO |  | 0% |  | 0% | 0%
|  | 29 | De-ethanizer column | FLNG-CM-SAS-BA-PER-PI-H-292 | NO | NO |  | 0% |  | 0% | 0%
|  | 30 | De-ethanizer reboiler | FLNG-CM-SAS-BA-PER-PI-H-293 | NO | NO |  | 0% |  | 0% | 0%
|  | 31 | De-ethanizer condenser & reflux drum | FLNG-CM-SAS-BA-PER-PI-H-294 | NO | NO |  | 0% |  | 0% | 0%
|  | 32 | De-ethanizer reflux pumps | FLNG-CM-SAS-BA-PER-PI-H-295 | NO | NO |  | 0% |  | 0% | 0%
|  | 33 | Propane compressor | FLNG-CM-SAS-BA-PER-PI-H-296 | NO | NO |  | 0% |  | 0% | 0%
|  | 34 | Stabiliser column | FLNG-CM-SAS-BA-PER-PI-H-300 | NO | NO |  | 0% |  | 0% | 0%
|  | 35 | Stabiliser reboiler | FLNG-CM-SAS-BA-PER-PI-H-301 | NO | NO |  | 0% |  | 0% | 0%
|  | 36 | Stabiliser condenser & reflux drum | FLNG-CM-SAS-BA-PER-PI-H-302 | NO | NO |  | 0% |  | 0% | 0%
|  | 37 | Stabiliser reflux pumps | FLNG-CM-SAS-BA-PER-PI-H-303 | NO | NO |  | 0% |  | 0% | 0%
|  | 38 | LPG pumps & metering | FLNG-CM-SAS-BA-PER-PI-H-304 | NO | NO |  | 0% |  | 0% | 0%
|  | 39 | Existing pig receiver liquid | FLNG-CM-SAS-BA-PER-PI-H-305 | NO | NO |  | 0% |  | 0% | 0%
|  | 40 | Existing condensate surge drum | FLNG-CM-SAS-BA-PER-PI-H-306 | NO | NO |  | 0% |  | 0% | 0%
|  | 41 | Existing condensate heater | FLNG-CM-SAS-BA-PER-PI-H-308 | NO | NO |  | 0% |  | 0% | 0%
|  | 42 | Existing condensate heater (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-309 | NO | NO |  | 0% |  | 0% | 0%
|  | 43 | Existing condensate storage tank | FLNG-CM-SAS-BA-PER-PI-H-400 | NO | NO |  | 0% |  | 0% | 0%
|  | 44 | Existing condensate storage tank (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-401 | NO | NO |  | 0% |  | 0% | 0%
|  | 45 | Condensate storage tank | FLNG-CM-SAS-BA-PER-PI-H-403 | NO | NO |  | 0% |  | 0% | 0%
|  | 46 | Existing storage export pumps | FLNG-CM-SAS-BA-PER-PI-H-405 | NO | NO |  | 0% |  | 0% | 0%
|  | 47 | Existing condensate export pumps (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-406 | NO | NO |  | 0% |  | 0% | 0%
|  | 48 | Condensate export pumps | FLNG-CM-SAS-BA-PER-PI-H-407 | NO | NO |  | 0% |  | 0% | 0%
|  | 49 | Existing condensate pig launcher | FLNG-CM-SAS-BA-PER-PI-H-408 | NO | NO |  | 0% |  | 0% | 0%
|  | 50 | Existing MVIA oil reception | FLNG-CM-SAS-BA-PER-PI-H-409 | NO | NO |  | 0% |  | 0% | 0%
|  | 51 | Produced water degasser | FLNG-CM-SAS-BA-PER-PI-H-450 | NO | NO |  | 0% |  | 0% | 0%
|  | 52 | Fuel gas scrubber | FLNG-CM-SAS-BA-PER-PI-H-500 | NO | NO |  | 0% |  | 0% | 0%
|  | 53 | Fuel gas heater, filter and distribution network | FLNG-CM-SAS-BA-PER-PI-H-501 | NO | NO |  | 0% |  | 0% | 0%
|  | 54 | Existing HP-LP fuel gas headers | FLNG-CM-SAS-BA-PER-PI-H-502 | NO | NO |  | 0% |  | 0% | 0%
|  | 55 | Existing HP-LP fuel gas headers (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-503 | NO | NO |  | 0% |  | 0% | 0%
|  | 56 | Existing fuel gas unit | FLNG-CM-SAS-BA-PER-PI-H-504 | NO | NO |  | 0% |  | 0% | 0%
|  | 57 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-505 | NO | NO |  | 0% |  | 0% | 0%
|  | 58 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-506 | NO | NO |  | 0% |  | 0% | 0%
|  | 59 | Existing CNG package | FLNG-CM-SAS-BA-PER-PI-H-507 | NO | NO |  | 0% |  | 0% | 0%
|  | 60 | Existing fire water storage tank | FLNG-CM-SAS-BA-PER-PI-H-601 | NO | NO |  | 0% |  | 0% | 0%
|  | 61 | Fire water network | FLNG-CM-SAS-BA-PER-PI-H-604 | NO | NO |  | 0% |  | 0% | 0%
|  | 62 | Fire water network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-605 | NO | NO |  | 0% |  | 0% | 0%
|  | 63 | Fire water pumps | FLNG-CM-SAS-BA-PER-PI-H-606 | NO | NO |  | 0% |  | 0% | 0%
|  | 64 | MEG regeneration package | FLNG-CM-SAS-BA-PER-PI-H-700 | NO | NO |  | 0% |  | 0% | 0%
|  | 65 | Existing meg storage tank | FLNG-CM-SAS-BA-PER-PI-H-701 | NO | NO |  | 0% |  | 0% | 0%
|  | 66 | Existing MEG pumps | FLNG-CM-SAS-BA-PER-PI-H-702 | NO | NO |  | 0% |  | 0% | 0%
|  | 67 | Existing Meg regeneration package | FLNG-CM-SAS-BA-PER-PI-H-711 | NO | NO |  | 0% |  | 0% | 0%
|  | 68 | Air compressor, air receiver,nitrogen genration package | FLNG-CM-SAS-BA-PER-PI-H-820 | NO | NO |  | 0% |  | 0% | 0%
|  | 69 | Instrument air distribution | FLNG-CM-SAS-BA-PER-PI-H-821 | NO | NO |  | 0% |  | 0% | 0%
|  | 70 | Existing instrument air network | FLNG-CM-SAS-BA-PER-PI-H-822 | NO | NO |  | 0% |  | 0% | 0%
|  | 71 | Existing air instrument/nitrogen production | FLNG-CM-SAS-BA-PER-PI-H-823 | NO | NO |  | 0% |  | 0% | 0%
|  | 72 | Existing instrument air network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-824 | NO | NO |  | 0% |  | 0% | 0%
|  | 73 | Nitrogen generation packages and nitrogen receiver (cancelled) | FLNG-CM-SAS-BA-PER-PI-H-830 | NO | NO |  | 0% |  | 0% | 0%
|  | 74 | Existing and new nitrogen network | FLNG-CM-SAS-BA-PER-PI-H-832 | NO | NO |  | 0% |  | 0% | 0%
|  | 75 | Existing nitrogen network (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-834 | NO | NO |  | 0% |  | 0% | 0%
|  | 76 | Existing diesel oil storage and transfer | FLNG-CM-SAS-BA-PER-PI-H-840 | NO | NO |  | 0% |  | 0% | 0%
|  | 77 | Existing diesel oil storage and transfer (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-841 | NO | NO |  | 0% |  | 0% | 0%
|  | 78 | Hot oil fired heater | FLNG-CM-SAS-BA-PER-PI-H-850 | NO | NO |  | 0% |  | 0% | 0%
|  | 79 | Hot oil expansion drum and pumps | FLNG-CM-SAS-BA-PER-PI-H-853 | NO | NO |  | 0% |  | 0% | 0%
|  | 80 | Hot oil filling system | FLNG-CM-SAS-BA-PER-PI-H-854 | NO | NO |  | 0% |  | 0% | 0%
|  | 81 | Chilling wtaer system A | FLNG-CM-SAS-BA-PER-PI-H-870 | NO | NO |  | 0% |  | 0% | 0%
|  | 82 | Chilling wtaer system B | FLNG-CM-SAS-BA-PER-PI-H-871 | NO | NO |  | 0% |  | 0% | 0%
|  | 83 | Cooling water pumps and expansion drum | FLNG-CM-SAS-BA-PER-PI-H-872 | NO | NO |  | 0% |  | 0% | 0%
|  | 84 | Corrosion inhibitor injection system | FLNG-CM-SAS-BA-PER-PI-H-891 | NO | NO |  | 0% |  | 0% | 0%
|  | 85 | HP & LP flare headers | FLNG-CM-SAS-BA-PER-PI-H-910 | NO | NO |  | 0% |  | 0% | 0%
|  | 86 | Existing LP flare header (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-912 | NO | NO |  | 0% |  | 0% | 0%
|  | 87 | Existing flare system | FLNG-CM-SAS-BA-PER-PI-H-913 | NO | NO |  | 0% |  | 0% | 0%
|  | 88 | HP flare KO drum, pumps and tip | FLNG-CM-SAS-BA-PER-PI-H-914 | NO | NO |  | 0% |  | 0% | 0%
|  | 89 | Existing LP flare header | FLNG-CM-SAS-BA-PER-PI-H-916 | NO | NO |  | 0% |  | 0% | 0%
|  | 90 | Existing LP flare header (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-917 | NO | NO |  | 0% |  | 0% | 0%
|  | 91 | Vent header and Tip (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-918 | NO | NO |  | 0% |  | 0% | 0%
|  | 92 | Vent header and Tip | FLNG-CM-SAS-BA-PER-PI-H-920 | NO | NO |  | 0% |  | 0% | 0%
|  | 93 | Open drain headers (cancelled) | FLNG-CM-SAS-BA-PER-PI-H-930 | NO | NO |  | 0% |  | 0% | 0%
|  | 94 | Existing open drain system | FLNG-CM-SAS-BA-PER-PI-H-932 | NO | NO |  | 0% |  | 0% | 0%
|  | 95 | Existing open drain system (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-933 | NO | NO |  | 0% |  | 0% | 0%
|  | 96 | Existing closed drain headers | FLNG-CM-SAS-BA-PER-PI-H-991 | NO | NO |  | 0% |  | 0% | 0%
|  | 97 | Existing closed drain headers (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-992 | NO | NO |  | 0% |  | 0% | 0%
|  | 98 | Closed drain headers | FLNG-CM-SAS-BA-PER-PI-H-993 | NO | NO |  | 0% |  | 0% | 0%
|  | 99 | Existing closed drain & flare KO drum | FLNG-CM-SAS-BA-PER-PI-H-994 | NO | NO |  | 0% |  | 0% | 0%
|  | 100 | Existing closed drain & flare KO drum (dismantling) | FLNG-CM-SAS-BA-PER-PI-H-995 | NO | NO |  | 0% |  | 0% | 0%

## EBOME
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER (old) | PID IDENTIFICATION NUMBER (new) | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[8 empty] | 100% | 100% | 100% | 100% | 100%
1 | BIPAGA | 1 | 12'' production line pig receiver A | FLNG-CM-SAS-BA-PER-PI-H-100 |  |  |  |  | 0% | 100% | 0% | 0%
2 | EBOME | 1 | Puits EBOME | EBM 003 | KCEBD004-CM-EP-PER-H018 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Monopodes | EBM 004 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Separateur 1er etage V101 A | EBM 005 | KCEBD004-CM-EP-PER-H001 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Separateur 1er etage V101 B | EBM 006 | KCEBD004-CM-EP-PER-H002 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Separateur 1er etage V101 C | EBM 007 | KCEBD004-CM-EP-PER-H003 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Separateur 1er etage V101 D | EBM 008 | KCEBD004-CM-EP-PER-H004 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Separateur 2ème etage | EBM 009 | KCEBD004-CM-EP-PER-H005 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Export huile | EBM 010 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Scrubber gaz V103 | EBM 011 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Manifold huile | EBM 012 | KCEBD004-CM-EP-PER-H016 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gaz lift | EBM 013 | KCEBD004-CM-EP-PER-H007 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Torche | EBM 014 | KCEBD004-CM-EP-PER-H008 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Traitement des eaux-SILLOS | EBM 015 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Drains | EBM 016 | KCEBD004-CM-EP-PER-H009 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Compresseur 2 ème etage | EBM 017 | KCEBD004-CM-EP-PER-H012 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Compresseur 1er etage | EBM 018 | KCEBD004-CM-EP-PER-H010 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Compresseur gas lift | / | KCEBD004-CM-EP-PER-H013 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Manifold gaz HP/BP | / | KCEBD004-CM-EP-PER-H014 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Manifold decompression GL | / | KCEBD004-CM-EP-PER-H016 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Eau de mer | EBM 019 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Reseau incendie | EBM 020 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Injection d'eau | EBM 021 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Bacs petrole generateurs | EBM 022 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Eau douce | EBM 023 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Circuit de refroidissement | EBM 024 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Air comprime | EBM 025 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Gazoil | EBM 026 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 28 | Ventilation | EBM 027 | / | NO | NO |  | 0% |  | 0% | 0%
|  | 29 | Dessableur | EBM 031 | / | NO | NO |  | 0% |  | 0% | 0%

## SANAGA 1
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% | 100% | 100% | 100% | 100%
1 | BIPAGA | 1 | 12'' production line pig receiver A | FLNG-CM-SAS-BA-PER-PI-H-100 |  |  |  | 0% | 100% | 0% | 0%
3 | SANAGA 1 | 1 | Well head 101 | FLN2-CM-SAS-S1-PER-PI-H-101 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Well head 102 | FLN2-CM-SAS-S1-PER-PI-H-102 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Well head 103 | FLN2-CM-SAS-S1-PER-PI-H-103 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | Well head 104 | FLN2-CM-SAS-S1-PER-PI-H-104 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | Well head 105 | FLN2-CM-SAS-S1-PER-PI-H-105 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | KB gas line pig receiver | FLN2-CM-SAS-S1-PER-PI-H-106 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | Existing production manifold | FLN2-CM-SAS-S1-PER-PI-H-109 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | New production manifold | FLN2-CM-SAS-S1-PER-PI-H-110 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | Free water knock out drum | FLN2-CM-SAS-S1-PER-PI-H-111 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Gas pig launcher to Bipaga | FLN2-CM-SAS-S1-PER-PI-H-112 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Gas cooling - SW exchanger | FLN2-CM-SAS-S1-PER-PI-H-113 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Temporary pig launcher and receiver skid | FLN2-CM-SAS-S1-PER-PI-H-115 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Well head 106 | FLN2-CM-SAS-S1-PER-PI-H-116 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Liquid/gas heat exchanger | FLN2-CM-SAS-S1-PER-PI-H-120 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Low temperature separator | FLN2-CM-SAS-S1-PER-PI-H-121 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Gas pig launcher | FLN2-CM-SAS-S1-PER-PI-H-122 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Gas heat exchanger | FLN2-CM-SAS-S1-PER-PI-H-123 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Produced water treatment | FLN2-CM-SAS-S1-PER-PI-H-130 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Manifolds for liquid export | FLN2-CM-SAS-S1-PER-PI-H-131 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Liquid export | FLN2-CM-SAS-S1-PER-PI-H-132 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Liquid export to EBOME | FLN2-CM-SAS-S1-PER-PI-H-133 | NO | NO |  | 0% |  | 0% | 0%
|  | 22 | Sea water lift pumps | FLN2-CM-SAS-S1-PER-PI-H-150 | NO | NO |  | 0% |  | 0% | 0%
|  | 23 | Offshore diesel | FLN2-CM-SAS-S1-PER-PI-H-160 | NO | NO |  | 0% |  | 0% | 0%
|  | 24 | Vent & closed drain system | FLN2-CM-SAS-S1-PER-PI-H-910 | NO | NO |  | 0% |  | 0% | 0%
|  | 25 | Drain tank and drain tank pump | FLN2-CM-SAS-S1-PER-PI-H-920 | NO | NO |  | 0% |  | 0% | 0%
|  | 26 | Chemical injection skid | FLN2-CM-SAS-S1-PER-PI-H-960 | NO | NO |  | 0% |  | 0% | 0%
|  | 27 | Vent collection network | FLN2-CM-SAS-S1-PER-PI-H-970 | NO | NO |  | 0% |  | 0% | 0%

## SANAGA 2
PID CENSUS
Plateform N° | Plateforms | N° | PID NAME | PID IDENTIFICATION NUMBER | Mark-up done | Offshore verification | PID MARKUP CHECKED |  | PID AUTOCAD VERSION |  | VERIFICATION SUR SITE APRES VERSION AUTOCAD
[7 empty] | 100% | 100% | 100% | 100% | 100%
1 | BIPAGA | 1 | 12'' production line pig receiver A | FLNG-CM-SAS-BA-PER-PI-H-100 |  |  |  | 0% | 100% | 0% | 0%
4 | SANAGA 2 | 1 | Battery limit sanaga-bridge | FLN2-CM-SAS-S1-PER-PI-H-005 | NO | NO |  | 0% |  | 0% | 0%
|  | 2 | Gas inlet air cooler | FLN2-CM-SAS-S1-PER-PI-H-006 | NO | NO |  | 0% |  | 0% | 0%
|  | 3 | Production separation | FLN2-CM-SAS-S1-PER-PI-H-008 | NO | NO |  | 0% |  | 0% | 0%
|  | 4 | LP turbocompressor sunction scrubber | FLN2-CM-SAS-S1-PER-PI-H-009-1 | NO | NO |  | 0% |  | 0% | 0%
|  | 5 | LP turbocompressor train A | FLN2-CM-SAS-S1-PER-PI-H-009-2 | NO | NO |  | 0% |  | 0% | 0%
|  | 6 | Gas air cooler-train A | FLN2-CM-SAS-S1-PER-PI-H-010-1 | NO | NO |  | 0% |  | 0% | 0%
|  | 7 | LP turbocompressor train B | FLN2-CM-SAS-S1-PER-PI-H-011 | NO | NO |  | 0% |  | 0% | 0%
|  | 8 | Gas air cooler-train B | FLN2-CM-SAS-S1-PER-PI-H-012 | NO | NO |  | 0% |  | 0% | 0%
|  | 9 | LP turbocompressor train C | FLN2-CM-SAS-S1-PER-PI-H-013 | NO | NO |  | 0% |  | 0% | 0%
|  | 10 | Gas air cooler-train C | FLN2-CM-SAS-S1-PER-PI-H-014 | NO | NO |  | 0% |  | 0% | 0%
|  | 11 | Booster compressor sunction scrubber | FLN2-CM-SAS-S1-PER-PI-H-014-2 | NO | NO |  | 0% |  | 0% | 0%
|  | 12 | Booster compressor for KPDC | FLN2-CM-SAS-S1-PER-PI-H-015 | NO | NO |  | 0% |  | 0% | 0%
|  | 13 | Fuel gas scrubber D-040 | FLN2-CM-SAS-S1-PER-PI-H-020 | NO | NO |  | 0% |  | 0% | 0%
|  | 14 | Fuel gas heater, filter and distribution network | FLN2-CM-SAS-S1-PER-PI-H-021 | NO | NO |  | 0% |  | 0% | 0%
|  | 15 | Air compressor, air receiver,nitrogen genration package | FLN2-CM-SAS-S1-PER-PI-H-022 | NO | NO |  | 0% |  | 0% | 0%
|  | 16 | Condensate export pumps | FLN2-CM-SAS-S1-PER-PI-H-025 | NO | NO |  | 0% |  | 0% | 0%
|  | 17 | Produced water degasser and pumps | FLN2-CM-SAS-S1-PER-PI-H-029 | NO | NO |  | 0% |  | 0% | 0%
|  | 18 | Emergency power generator | FLN2-CM-SAS-S1-PER-PI-H-090 | NO | NO |  | 0% |  | 0% | 0%
|  | 19 | Main power generator TG-2002B | FLN2-CM-SAS-S1-PER-PI-H-200 | NO | NO |  | 0% |  | 0% | 0%
|  | 20 | Sea water fire fighting pumps | FLN2-CM-SAS-S1-PER-PI-H-250 | NO | NO |  | 0% |  | 0% | 0%
|  | 21 | Offshore diesel | FLN2-CM-SAS-S1-PER-PI-H-260 | NO | NO |  | 0% |  | 0% | 0%